## Examples of risks
Technical/engineering issues | Personell issues | Partner issues | Financial issues | Other issues | Scientific issues
New technological breaktroughs that make the project obsolete | Loss of Key personel | Partner is not competent to carry out allocated tasks | Major exchange rate fluctuations or price inflation lead to partner beeing unable to fufill it's comitments | Data governance compliance failure | Lack of strategic data on time
Project technological proved to be unfeasable | Personell leave before the end of the project | partner declare bancrupcy | Costs increase leeds to inability to get nessecary eqiptment/access | New legislation affect ability to complete project | Insufficent quality of obtained data
Failure to obtain nessecary resourses/tools/hardware/ip rights | Conflict between project members | Partner experience take over and shift in priorities |  | Insufficient community engagement | unability to recruit human subjects
Code owners and tool developers fail to reach consensus on solution strategy. |  | Partner withdraw from Project |  | Damage to the reputation of the project from lack of trust or failure to engage and communicate with external scientific and public communities. | unability to obtain ethical permissions
External organisations patents key elements of the planned technology |  | Major exchange rate fluctuations or price inflation |  | Project will not lead to exploitable results/products | Poor interaction between WP/research groups
Delays in key parts of software/hardware development |  | Conflict between partners |  | Travel restrictions prevent/delay/lower partcipitation in events/training/conferences etc | Data is stored in non approved locations
Support/availability of external software/part of software is discontinued or made obsolete |  | Poor interaction between parters |  | Change in legislation hinder used tools for data storage/sharing/collaboration | GDPR is breached
Requirements are poorly defined
Technical work is more compex than estimated
Poor interaction between WP/research groups
Used tools not/no longer allowed

## Project risk registry
# | Risk Type | Description of risk | Effects of Risk Materialising | WP(s) first impacted by risk materialising | Proposed mitigation measures | Risk tracker | Probability of risk materialising | Impact of risk materialising | Risk Priority Level | Evaluation Frequency | Last evaluated | Column2 | Risk Materialised? | Mitigation Measures Applied? | Actions Taken | In the Portal?
1 | Technical Risk | Desc 1 | Eff 1 |  |  | Partner 1 | Low | High | Medium | Every 5 months |  | TRUE |  |  |  | YES
2 | Technical Risk | Desc 2 | Eff 2 |  |  | Partner 2 | Low | High | Medium | Every 5 months |  | TRUE |  |  |  | YES
3 | Technical Risk | Desc 3 | Eff 3 |  |  | Partner 3 | Low | High | Medium | Every 5 months |  | TRUE |  |  |  | YES
4 | Management Risk | Desc 4 | Eff 4 |  |  | Partner 4 | Medium | Medium | Medium | Every 5 months |  | TRUE |  |  |  | YES
5 | Technical Risk | Desc 5 | Eff 5 |  |  | Partner 5 | Medium | Medium | Medium | Every 5 months |  | TRUE |  |  |  | YES
6 | External Risk | Desc 6 | Eff 6 |  |  | Partner 6 | Medium | Medium | Medium | Every 5 months |  | TRUE |  |  |  | YES
7 | Time Risk | Desc 7 | Eff 7 |  |  | Partner 7 | Medium | Low | Low | Every 7 months |  | TRUE |  |  |  | YES
8 | Management Risk | Desc 8 | Eff 8 | [8 empty] | #VALUE! |  |  |  | YES
9 | [11 empty] | #VALUE! |  |  |  | YES
10 | [11 empty] | #VALUE! |  |  |  | YES
11 | [11 empty] | #VALUE! |  |  |  | YES
12 | [11 empty] | #VALUE!
13 | [11 empty] | #VALUE!
14 | [11 empty] | #VALUE!
15 | [11 empty] | #VALUE!
16 | [11 empty] | #VALUE!
17 | [11 empty] | #VALUE!
18 | [11 empty] | #VALUE!
19 | [11 empty] | #VALUE!
20 | [11 empty] | #VALUE!
21 | [11 empty] | #VALUE!
22 | [11 empty] | #VALUE!
23 | [11 empty] | #VALUE!
24 | [11 empty] | #VALUE!
25 | [11 empty] | #VALUE!
26 | [11 empty] | #VALUE!
27 | [11 empty] | #VALUE!
28 | [11 empty] | #VALUE!
29 | [11 empty] | #VALUE!
30 | [11 empty] | #VALUE!
31 | [11 empty] | #VALUE!
32 | [11 empty] | #VALUE!
33 | [11 empty] | #VALUE!
34 | [11 empty] | #VALUE!
35 | [11 empty] | #VALUE!
36 | [11 empty] | #VALUE!
37 | [11 empty] | #VALUE!
38 | [11 empty] | #VALUE!
39 | [11 empty] | #VALUE!
40 | [11 empty] | #VALUE!
41 | [11 empty] | #VALUE!
42 | [11 empty] | #VALUE!
43 | [11 empty] | #VALUE!
44 | [11 empty] | #VALUE!
45 | [11 empty] | #VALUE!
46 | [11 empty] | #VALUE!
47 | [11 empty] | #VALUE!
48 | [11 empty] | #VALUE!
49 | [11 empty] | #VALUE!
50 | [11 empty] | #VALUE!
Formulas:
Column2 = EDATE(TODAY(),-IFERROR(VLOOKUP((VLOOKUP([Probability of risk materialising],'risk level data'!A$2:B6,2,FALSE())*VLOOKUP([Impact of risk materialising],'risk level data'!D$2:E6,2,FALSE())),'risk level data'!G$2:I14,3,FALSE()),""))>Table1[[#This Row],[Last evaluated]]

## risk level data
Probability |  | Impact |  | Priority |  |  | Type
Low | 1 | Low | 1 | 1 | Low | 9 | Management Risk
Medium | 3 | Medium | 3 | 3 | Low | 7 | Time Risk
High | 5 | High | 5 | 5 | Medium | 5 | Competence Risk
|  |  |  | 9 | Medium | 5 | Technical Risk
|  |  |  | 15 | High | 3 | External Risk
|  |  |  | 25 | High | 1

## Sheet1 (hidden)
Impact
|  | Negligible | Minor | Moderate | Significant | Severe
Probability | Rare | Minimum | Minimum | Minimum | Low | Low
| Unlikely | Minimum | Low | Low | Moderate | Moderate
| Moderate | Minimum | Low | Moderate | High | High
| Likely | Low | Moderate | High | High | Extreme
| Almost Certain | Low | Moderate | High | Extreme | Extreme
[7 empty] | Priority | Evaluation frequency
[7 empty] | Minimum | Every 9 months
[7 empty] | Low | Every 7 months
[7 empty] | Moderate | Every 5 months
[7 empty] | High | Every 3 months
[7 empty] | Extreme | Every 1 months